## WBS
Project Title: | Project 1 - Multi-server Network
Members: | Yirun Pan, Ning Kang, Nannan Gu, Wenyi Zhao
Prepared by: | Ning Kang
Issued Date | 2018-04-13
Element Number | WBS Elements Activity, Task, or Sub-Task Name | Definition of Activity or Task (Description) | Responsible Person or Group | Effect (days) | Work Type | Assign Date | Status | Update Date
1 | Architecture Design | Detail design of the system | Ning Kang | 4 | Design | 2018-03-29 | Done | 2018-04-13
2 | User Skeleton Implemention | Client command args, input validations and connection estimation | Yiru Pan | 2 | coding | 2018-03-29 | Done | 2018-04-13
3 | User Register Handlers of Client | RegisterSuccHandler RegisterFailedHandler |  |  | coding | 2018-04-13 | Done | 2018-04-16
4 | User Login Handlers of Client | LoginSuccHandler LoginFailedHandler RedirectHandler |  |  | coding | 2018-04-13 | Done | 2018-04-16
5 | Other Handlers of Client | ClientInvalidHandler ClientAuthenFailedHandler ClientActivityBroadcastHandler |  |  | coding | 2018-04-13 | Done | 2018-04-16
6 | User Register Handlers of Server | UserRegisterHandler LockRequestHandler LockAllowedHandler LockDeniedHandler BroadcastResult | NIng Kang | 2 | coding | 2018-04-13 | Done | 2018-04-16
7 | User Login Handlers of Server | UserEnquiryHandler UserFoundHandler UserLoginHandler UserLogoutHandler | Ning Kang | 2 | coding | 2018-04-13 | Done | 2018-04-16
8 | Server authen Handlers of Server | ServerAuthenFailedHandler ServerAuthenRequestHandler | Nannan Gu | 2 | coding | 2018-04-13 | Done | 2018-04-16
9 | Activitiy Handlers of Server | ActivityBroadcastHandler ActivityRequestHandler | Nannan Gu | 2 | coding | 2018-04-13 | Done | 2018-04-16
10 | Load Announce of Server | ServerAnnounceHandler | Nannan Gu | 2 | coding | 2018-04-13 | Done | 2018-04-16
11 | Other Server side Handlers | ServerInvalidHandler | NIng Kang | 1 | coding | 2018-04-13 | Done | 2018-04-16
12 | Test case design | Design test cases based on reguirement | Ning Kang | 1 | Design | 2018-04-15 | Done | 2018-04-16
13 | Testing of Functionality of Server Auth | All related behaviours of server auth, only Server side | Yiru Pan | 1 | Testing | 2018-04-16 | In progress | 2018-04-16
14 | Testing of Functionality of Register | All related behaviours of user register, includes both Sever side and Client side | Nannan Gu | 1 | Testing | 2018-04-16 | In progress | 2018-04-16
15 | Testing of Functionality of Login | All related behaviours of user login includes both Sever side and Client side | Wenyi Zhao | 1 | Testing | 2018-04-16 | In progress | 2018-04-16
16 | Testing of Functionality of Logout | All related behaviours of user logout includes both Sever side and Client side | Wenyi Zhao | 1 | Testing | 2018-04-16 | In progress | 2018-04-16
17 | Testing of Functionality of Load Announce | All related behaviours of load announce, only Server side | Ning Kang | 1 | Testing | 2018-04-16 | In progress | 2018-04-16
18 | Testing of Functionality of Redirection | All related behaviours of redirection, includes both Sever side and Client side | Ning Kang | 1 | Testing | 2018-04-16 | In progress | 2018-04-16
19 | Testing of Functionality of Activity | All related behaviours of sending/receiving activities, includes both Sever side and Client side | Ning Kang | 1 | Testing | 2018-04-16 | In progress | 2018-04-16
20 | Documentation - Readme.md | How to use this system and the basic logic of implementing functionalities | Ning Kang | 1 |  |  | Pending | 2018-04-16
21 | Analysis - Server Failure Model |  | Wenyi Zhao | 0.5 |  |  | Pending | 2018-04-16
22 | Analysis - Concurrency issues |  | Nannan Gu | 0.5 |  |  | Pending | 2018-04-16
23 | Analysis - Scalability |  | Yiru Pan | 0.5 |  |  | Pending | 2018-04-16
Total |  |  |  | 27.5